## Snapshot 24-8
IT Simplification — FY27 Cost-out Dashboard
Actual savings achieved, remaining opportunity and timing by quarter
V1 BUDGET |  |  | ENTERED RENEWAL PRICE |  |  | NET IDENTIFIED COSTOUT |  | FINALISED POSITIVE COSTOUT
23692506.4576 |  |  | 22882202.2292 |  |  | 809748.4476 |  | 614081.4044
The tracked V1 budget is $23,692,506 and entered renewal prices total $22,882,202. The signed net identified costout in Column J is $809,748. Of the $1,088,785 gross positive costout identified, $614,081 is finalised (56.4%); $279,037 is separately classified as budget variance / reclassification.
QUARTERLY BUDGET, RENEWAL AND COSTOUT OUTLOOK
Metric | Q1 FY27 | Q2 FY27 | Q3 FY27 | Q4 FY27 | Unscheduled | FY27 Total
V1 budget | 844008.1728 | 3477136.3067 | 1175842.5 | 1272025.91 | 16923493.5682 | 23692506.4576
Entered renewal price | 571403.04 | 3370256.43 | 1170789.8692 | 1264749.73 | 16505003.16 | 22882202.2292
Net identified costout | 272605.1328 | 106879.8767 | 4496.85 | 7276.18 | 418490.4082 | 809748.4476
Finalised positive costout | 254862.6828 | 31865.27 | 1788.49 | 0 | 325564.9616 | 614081.4044
Unfinalised positive costout | 20331.69 | 105157.0067 | 3088.36 | 48881.52 | 297245.4532 | 474704.0298
Budget variance / reclassification | 2589.24 | 30142.4 | 380 | 41605.34 | 204320.0067 | 279036.9867
CATEGORY BUDGET, RENEWAL AND COSTOUT OUTLOOK
Category | V1 budget | Entered renewal price | Net identified costout | Finalised positive costout | Unfinalised positive costout | Budget variance / reclassification
Licensing | 7231432.4311 | 6533550.6492 | 697326.0011 | 559584.4044 | 212458.5767 | 74716.98 |  | Net identified costout: Overall expected reduction based on all values currently entered
Consumption | 7659712.8426 | 7606351.84 | 53361.0026 | 54497 | 3184.0026 | 4320 |  | Finalised positive costout: Savings confirmed/completed
New Spend | 458748.67 | 458748.67 | 0 | 0 | 0 | 0 |  | Unfinalised positive costout: Savings pipeline - not guaranteed savings
Microsoft | 8342612.5139 | 8283551.07 | 59061.4439 | 0 | 259061.4506 | 200000.0067 |  | Budget variance: New $$ added in
Total | 23692506.4576 | 22882202.2292 | 809748.4476 | 614081.4044 | 474704.0298 | 279036.9867
Definitions: Net identified costout = the signed total of Column J across Licensing, Consumption, New Spend and Microsoft. Gross positive costout = positive Column J only. Finalised positive costout = positive Column J where Finalised? is Y. Budget variance / reclassification = the absolute value of negative Column J. Entered renewal price sums values currently populated in Column I. Data note: 6 tracked renewal-price cells are blank, covering $91,963 of V1 budget.
Licensing cost-out to date
Vendor | Contract | V1 budget | Renewal price | Costout |  | Committed summary | V1 budget | Renewal price | Costout
China Telecom Global Limited | AWS Network Circuit - Singapore to Shanghai | 31644 | 0 | 31644 |  | 25 committed items | 1101890.6144 | 542306.21 | 559584.4044
Digital Maas Pty Ltd | SEO Tool - Premium Subscription | 33330.3616 | 0 | 33330.3616
Dragon Metrics Limited | Dragon Metrics Subscription – Enterprise (Weekly ranking update) | 13440 | 0 | 13440
Happy Scribe | 0 | 588 | 0 | 588
Walkme for SAP | 0 | 187065.6 | 0 | 187065.6
Xtremepush Ltd | 0 | 5000 | 0 | 5000
Survey Monkey | 0 | 2.8457 | 0 | 2.8457
ContactMonkey | Outlook Add-In | 44383.56 | 21315 | 23068.56
Microway (Vyond) | Vyond Professional Annual - Single User | 4748.9171 | 0 | 4748.9171
App Samurai Limited | Storyly | 16835.05 | 0 | 16835.05
Creatify Lab Inc | Creatify Unlimited Team Plan (10 seats) | 18158.9 | 13921 | 4237.9
LinkedIn Singapore Pte Ltd | LinkedIn Talent Insights - Commerical ProServ (213 inv # 51110651342 ) | 354869.79 | 166469 | 188400.79
Similarweb Australia Pty Ltd | PRO Service - Digital Marketing Suite - Ultimate (Aus Contract) | 145598 | 141000 | 4598
Realtimeboard Inc. dba Miro | Miro - Enterprise License Plan 200 users | 89342.25 | 81676 | 7666.25
Adjust GmbH | Adjust Core - 1,000,000 Conversions | 21602.37 | 16705 | 4897.37
Data#3 Limited | Last Pass Subscription (Password Software Mgt) IAM Team | 20822.12 | 20822.12 | 0
APNIC Pty Ltd | Annual Membership | 2116 | 1709 | 407
Interactive Pty Ltd | Hardware Maintenance Renewal | 29440 | 27511 | 1929
IP2Location | IP2Location Web Service (5,000,000 Credits) | 1771.24 | 0 | 1771.24
Vimeo.com, INC | Vimeo Custom - Entry Level (44645097) | 12185.9 | 6116 | 6069.9
Data#3 Limited | TechSmith Camtasia licenses | 300.42 | 208 | 92.42
WP Engine | Hosting services, Secure Hosting Growth Plan | 12400.71 | 0 | 12400.71
Interactive Pty Ltd | UPS Maintenance Renewal | 9602 | 0 | 9602
Hello Teams Pty Ltd | HO - Australia | 44854.09 | 44854.09 | 0
IP2Location | IP2Proxy Web Service (500,000 Credits) | 1788.49 | 0 | 1788.49
Upcoming licensing vendors
Vendor | Contract | Contract date | V1 budget | Renewal price | Costout | Licensing summary | V1 budget | Renewal price | Costout
Freepik Company, SL | Freepik Premium+ Yearly | 06-Aug-26 | 10897.62 | 10897.62 | 0 | 60 uncommitted items | 6129541.8167 | 5991244.4392 | 137741.5967
EPI-USE Australia Pty Ltd | SuccessFactor Support - for global payroll integrations | 08-Sep-26 | 6959.34 | 6959.34 | 0
Insight Enterprises Australia Pty Ltd | Cerberus FTP Server (Not in Budget) | 11-Sep-26 | 4000 | 3928.96 | 71.04
Data#3 Limited | Adobe 1yr Licenses (2xCC) | 12-Sep-26 | 3496.56 | 0 | 3496.56
Data#3 Limited | Adobe 1yr Licenses (9xCC,1xAP) | 12-Sep-26 | 16764.09 | 0 | 16764.09
MightyHive AU PTY LTD | GA4 360 License | 30-Sep-26 | 83410.76 | 86000 | -2589.24
Maxmind Inc | IP address geolocation using accurate GeoIP® data. | 09-Oct-26 | 2558.56 | 2558.56 | 0
AWS Marketplace - Cloudec | Managed Services | 02-Nov-26 | 63000 | 63000 | 0
Voucherify P.S.A | Discount Code Software | 14-Nov-26 | 62507 | 62507 | 0
Award Force Pty Ltd | Awards Management Platform - to Manage Award Programs | 28-Nov-26 | 15442.02 | 15442.02 | 0
Learning Seat Pty Ltd | Litmos Content, ANZ Compl Ed Standalone | 29-Nov-26 | 22489.93 | 22489.93 | 0
Lucid Software Inc. | Lucide Suite x 83 | 30-Nov-26 | 55533.21 | 55533.21 | 0
Elemenator | 0 | 04-Dec-26 | 0 | 142.4 | -142.4
Appointlet | 0 | 08-Dec-26 | 16000 | 10780.5 | 5219.5
Sap Australia Pty Ltd | BTP Enterprise Agreement (213BTI) | 08-Dec-26 | 38169.86 | 38169.86 | 0
FRAUDWATCH INTERNATIONAL PTY LTD | Digital Brand Protection | 12-Dec-26 | 72737.12 | 72737.12 | 0
FastSpring | Numbeo API Basic Plan - living database | 15-Dec-26 | 7767.45 | 6000 | 1767.45
Vimeo.com, INC | Video sharing platform (IELTS) | 16-Dec-26 | 513 | 513 | 0
One Trust Australia Pty Ltd | GRC Tooling Cloud License - Risk Management | 17-Dec-26 | 83640.9 | 83640.9 | 0
AWS Marketplace - Splunk | Splunk Cloud Subscription | 22-Dec-26 | 819389.08 | 819389.08 | 0
AWS Marketplace - Splunk | Splunk Observability | 22-Dec-26 | 114542.94 | 144542.94 | -30000
Adobe Systems Software Ireland Limited | Marketo - Student Placement (Year 1- 1.2M, Year 2- $1.5M, Year 3- $1.7M) | 31-Dec-26 | 1806000 | 1806000 | 0
Adobe Systems Software Ireland Limited |  | 31-Dec-26 | 76651.4367 | 0 | 76651.4367
CISO Lens Pty Ltd | CISO Lens Membership - Simon Cowley, Rosie, AMG | 31-Dec-26 | 74680.82 | 74680.82 | 0
Ionic Inc. | 2 seats 2 concurrent builds 1.3M updates - IDP IELTS | 31-Dec-26 | 24773.62 | 13440 | 11333.62
Sap Australia Pty Ltd | SAP C4C V2 POC | 31-Dec-26 | 10185 | 0 | 10185
AWS Marketplace - Marketo | Marketo Engage | 05-Jan-27 | 836817.43 | 836817.43 | 0
Burst Training and Design | 19 x Articulate 360 TEAMs Annual Subscription - (Tech 2 licenses). | 14-Jan-27 | 43880.53 | 43880.53 | 0
Wordfence | idpielts.me, iknow.ielts.idp.com | 14-Jan-27 | 678.87 | 678.87 | 0
Screaming Frog | 0 | 19-Jan-27 | 2474.14 | 2474.14 | 0
Hubspot Australia PTY LTD | HubSpot - Marketing Hub Starter+G58 | 20-Jan-27 | 0 | 0 | 0
Supermetrics | Supermetrics - Hub | 21-Jan-27 | 85828.33 | 85828.33 | 0
Apple Inc. | DC Apple Developer Account - IDP Connect (Lower enviroment) | 25-Jan-27 | 420 | 179.5068 | 0
TeamViewer Germany GmbH | Remote access tool | 22-Feb-27 | 8702 | 8702 | 0
ZOHO Corporation | Site24x7 | 09-Mar-27 | 3088.36 | 0 | 3088.36
Mentimeter | 2 x Mentimeter pro licenses | 12-Mar-27 | 500 | 880 | -380
Time Target Pty Ltd | Humanforce T&A system for AU/NZ, | 16-Mar-27 | 75140.08 | 75140.08 | 0
C A Technology Pty Ltd (CAMMS) | CAMMS GRC Tool | 30-Mar-27 | 116104.27 | 116104.27 | 0
Apple Inc. | DC Apple Developer Account | 31-Mar-27 | 420 | 104.7123 | 0
UXCam Inc. | Mobile App analytics tool | 03-Apr-27 | 40335.34 | 40335.34 | 0
IPQS | IPQS SMB+ Enterprise Feature with Monthly IP Lookup (75,000) | 20-Apr-27 | 24960 | 24960 | 0
AWS Marketplace – Docker Inc | SW subscription Docker Business Plan | 27-Apr-27 | 23040 | 23040 | 0
CSC Corporate Domains, Inc. | Domain Registrations | 30-Apr-27 | 50400 | 30518.48 | 19881.52
Equinix Australia Pty Ltd | Saas - data center services | 30-Apr-27 | 52500 | 52500 | 0
DataEDO | Dataedo Starter (3 editors + unlimited viewers / community users) | 04-May-27 | 13600 | 13600 | 0
Mobbin.com | 0 | 09-May-27 | 0 | 691.2 | -691.2
ExpressVPN | 0 | 13-May-27 | 0 | 162.14 | -162.14
Interactive Pty Ltd | IBM Hardware and Software Maintenance Renewal (25%) | 17-May-27 | 158909.97 | 158909.97 | 0
Interactive Pty Ltd | IBM Hardware and Software Maintenance Renewal (75%) | 17-May-27 | 566888.67 | 566888.67 | 0
Convert Insights Inc. | Convert A/B testing Enterprise Plan | 21-May-27 | 41901.42 | 41901.42 | 0
Zoom Video Communications Inc | Zoom Licenses | 31-May-27 | 131371.72 | 131371.72 | 0
Import.io | SaaS Premium Plan (1M Query) | 01-Jun-27 | 45000 | 16000 | 29000
Figma, Inc. | Organization Full seats x 15 | 02-Jun-27 | 16929.2 | 16929.2 | 0
SonarSource SA | Quote_SonarQube Enterprise Edition Up to 10M Lines of Code | 04-Jun-27 | 86189.59 | 86189.59 | 0
ElevenLabs | Elevenlabs Enterprise Subscription - AI Voice | 11-Jun-27 | 0 | 0 | 0
Ahrefs Pte Ltd | Ahrefs Enterprise user Yearly | 30-Jun-27 | 20000 | 60752 | -40752
AWS Marketplace – IBM Software | IBM Cloudability Subscription renwal by Cloudec | 0 | 75000 | 40000 | 35000
Connect Managed Services (UK) Ltd | Service to Connect MTN’s SIP service to IDP’s PureCloud Software (Genesys Cloud) in Ghana (weconnect) | 0 | 0 | 0 | 0
TPG Telecom | Blanket PO for FY27 Monthly Invoices | 0 | 116179.08 | 116179.08 | 0
Verona Labs | WP Statistics Premium - Single Site - analytics plugin we use for iKnow | 0 | 172.5 | 172.5 | 0
Consumption cost-out to date
Vendor | Contract | V1 budget | Renewal price | Costout |  | Committed summary | V1 budget | Renewal price | Costout
Amazon Web Services Australia Pty Ltd |  | 5687336 | 5687336 | 0 |  | 16 committed items | 7429202 | 7374705 | 54497
AWS Marketplace - Anthropic PBC |  | 302217 | 302217 | 0
AWS Marketplace - ClamAV | BucketAV Software | 3630 | 3630 | 0
AWS Marketplace - N2WS | Aws Backups | 9600 | 9600 | 0
AWS Marketplace – NGINX Software | Load balancer | 15000 | 15000 | 0
BitTitan |  | 497 | 0 | 497
Bulk SMS | SMS Alerts for PRTG it.accounts@idp.com www.bulksms.com | 0 | 0 | 0
Civica Pty Ltd |  | 973271.2 | 973271.2 | 0
Google Australia Pty Ltd | DC, Google Workspaces, IELTS - James Rich | 24000 | 24000 | 0
Google Australia Pty Ltd | Google Recaptcha | 2000 | 2000 | 0
Gupshup |  | 14000 | 0 | 14000
Interactive Pty Ltd | UPS Servicing | 40000 | 0 | 40000
IVE Group Australia Pty Ltd |  | 296008 | 296008 | 0
LiveAgent | Service Desk platform the IELTS Customer Support Team | 20620.8 | 20620.8 | 0
SafetyCulture (iAuditor) |  | 11550 | 11550 | 0
Upstream Print Solutions Pty Ltd |  | 29472 | 29472 | 0
Upcoming consumption vendors
Vendor | Contract | V1 budget | Renewal price | Costout |  | Upcoming summary | V1 budget | Renewal price | Costout
Beijing Sinnet Technology Co., Ltd. | Intermediary for AWS China | 31886.8426 | 31886.84 | 0.0025894 |  | 8 uncommitted items | 230510.8426 | 231646.84 | -1135.9974
Growthbook | Growthbook Cloud x 4 | 3024 | 240 | 2784
Mapbox Inc | Location Data Platform - 3 accounts (SP, DM, LT) | 18000 | 18000 | 0
OpenAI |  | 100000 | 100000 | 0
Sinch Australia Pty Ltd | CPaaS | 42000 | 42000 | 0
Sinch UK Ltd. | CPaaS | 28000 | 28000 | 0
Stackify LLC |  | 7200 | 11520 | -4320
Zapier | Zapier - Pro Plan | 400 | 0 | 400
New Spend cost-out to date
Vendor | Contract | V1 budget | Renewal price | Costout |  | Committed summary | V1 budget | Renewal price | Costout
No committed new spend items | [5 empty] | 0 committed items | 0 | 0 | 0
Upcoming new spend vendors
Vendor | Contract | V1 budget | Renewal price | Costout |  | Upcoming summary | V1 budget | Renewal price | Costout
Contenful Nine Tail Personalisation |  | 100000 | 100000 | 0 |  | 10 uncommitted items | 458748.67 | 458748.67 | 0
Envato Elements |  | 7830 | 7830 | 0
Google support |  | 875 | 875 | 0
LLM |  | 10000 | 10000 | 0
NaturalReader |  | 1377 | 1377 | 0
New EA Tool |  | 80000 | 80000 | 0
NOOSR |  | 2000 | 2000 | 0
SANS |  | 50000 | 50000 | 0
Smartly IO |  | 186666.67 | 186666.67 | 0
TBC |  | 20000 | 20000 | 0
Microsoft cost-out to date
Vendor | Contract | V1 budget | Renewal price | Costout |  | Committed summary | V1 budget | Renewal price | Costout
No committed Microsoft items | [5 empty] | 0 committed items | 0 | 0 | 0
Upcoming Microsoft vendors
Vendor | Contract | V1 budget | Renewal price | Costout |  | Upcoming summary | V1 budget | Renewal price | Costout
Data#3 Limited | M365 (342) + O365 (310) Education Licenses | 9951.694 | 0 | 9951.694 |  | 22 uncommitted items | 8342612.51 | 8283551.07 | 59061.44
Data#3 Limited | Info River | 5359.7358 | 0 | 5359.7358
Insight Enterprises Australia Pty Ltd | Microsoft 365 Copilot x 200 | 113148 | 113148 | 0
Insight Enterprises Australia Pty Ltd | Microsoft 365 Copilot x 128 | 66087.33 | 66087.33 | 0
Insight Enterprises Australia Pty Ltd | Office 365 x Extra Storage x 15000 | 105300 | 105300 | 0
Insight Enterprises Australia Pty Ltd | Windows 365 Enterprise 4 vCPU, 16 GB, 128 GB x 20 | 32601.6 | 32601.6 | 0
Insight Enterprises Australia Pty Ltd | Windows 365 Enterprise 8 vCPU, 32 GB, 256 GB x 15 | 93340.8 | 93340.8 | 0
Insight Enterprises Australia Pty Ltd | Microsoft Visual Studio Pro MSDN ALng LSA | 0 | 0 | 0
Microsoft Pty Ltd |  | 243750 | 0 | 243750
Microsoft Pty Ltd | AZURE montly charges | 121394.16 | 121394.16 | 0
Microsoft Pty Ltd | Defender | 302982.0164 | 302982.02 | -0.0035616
Microsoft Pty Ltd | Enterprise Agreement (Corp Portion 30%) | 2052892.6321 | 2052892.63 | 0.0020548
Microsoft Pty Ltd | Enterprise Agreement (SP Portion 70%) | 4790082.8048 | 4790082.8 | 0.0047671
Microsoft Pty Ltd | Intune licence | 156240 | 156240 | 0
Microsoft Pty Ltd | Licenses and Software Assurance (Corp Portion 30%) | 8257.445 | 8257.44 | 0.0049973
Microsoft Pty Ltd | Licenses and Software Assurance (SP Portion 70%) | 19259.3717 | 19259.37 | 0.0016603
Microsoft Pty Ltd | Reservations | 29236.7198 | 29236.72 | -0.00021918
Microsoft Pty Ltd | SQL Server (Corp Portion 30%) | 43215.1092 | 43215.11 | -0.00075205
Microsoft Pty Ltd | SQL Server (SP Portion 70%) | 100835.2479 | 100835.25 | -0.0021192
Microsoft Pty Ltd | Teams Software | 11134.4627 | 11134.46 | 0.0026849
Microsoft Pty Ltd | Windows 10 ESU | 37543.3846 | 37543.38 | 0.0046154
Silverleaf Solutions Australia Pty Ltd | Microsoft EA Advisory | 0 | 200000 | -200000

## Snapshot 17-8
IT Simplification — FY27 Cost-out Dashboard
Actual savings achieved, remaining opportunity and timing by quarter
V1 BUDGET |  |  | ENTERED RENEWAL PRICE |  |  | NET IDENTIFIED COSTOUT |  | FINALISED POSITIVE COSTOUT
23692506.4576 |  |  | 22938225.9592 |  |  | 753724.7176 |  | 556024.6744
The tracked V1 budget is $23,692,506 and entered renewal prices total $22,938,226. The signed net identified costout in Column J is $753,725. Of the $1,028,442 gross positive costout identified, $556,025 is finalised (54.1%); $274,717 is separately classified as budget variance / reclassification.
QUARTERLY BUDGET, RENEWAL AND COSTOUT OUTLOOK
Metric | Q1 FY27 | Q2 FY27 | Q3 FY27 | Q4 FY27 | Unscheduled | FY27 Total
V1 budget | 844008.1728 | 3477136.3067 | 1175842.5 | 1272025.91 | 16923493.5682 | 23692506.4576
Entered renewal price | 571403.04 | 3372027.67 | 1172578.3592 | 1264749.73 | 16557467.16 | 22938225.9592
Net identified costout | 272605.1328 | 105108.6367 | 2708.36 | 7276.18 | 366026.4082 | 753724.7176
Finalised positive costout | 254862.6828 | 30094.03 | 0 | 0 | 271067.9616 | 556024.6744
Unfinalised positive costout | 20331.69 | 105157.0067 | 3088.36 | 48881.52 | 294958.4532 | 472417.0298
Budget variance / reclassification | 2589.24 | 30142.4 | 380 | 41605.34 | 200000.0067 | 274716.9867
CATEGORY BUDGET, RENEWAL AND COSTOUT OUTLOOK
Category | V1 budget | Entered renewal price | Net identified costout | Finalised positive costout | Unfinalised positive costout | Budget variance / reclassification
Licensing | 7231432.4311 | 6537110.3792 | 693766.2711 | 556024.6744 | 212458.5767 | 74716.98 |  | Net identified costout: Overall expected reduction based on all values currently entered
Consumption | 7659712.8426 | 7658815.84 | 897.0026 | 0 | 897.0026 | 0 |  | Finalised positive costout: Savings confirmed/completed
New Spend | 458748.67 | 458748.67 | 0 | 0 | 0 | 0 |  | Unfinalised positive costout: Savings pipeline - not guaranteed savings
Microsoft | 8342612.5139 | 8283551.07 | 59061.4439 | 0 | 259061.4506 | 200000.0067 |  | Budget variance: New $$ added in
Total | 23692506.4576 | 22938225.9592 | 753724.7176 | 556024.6744 | 472417.0298 | 274716.9867
Definitions: Net identified costout = the signed total of Column J across Licensing, Consumption, New Spend and Microsoft. Gross positive costout = positive Column J only. Finalised positive costout = positive Column J where Finalised? is Y. Budget variance / reclassification = the absolute value of negative Column J. Entered renewal price sums values currently populated in Column I. Data note: 7 tracked renewal-price cells are blank, covering $91,963 of V1 budget.
Licensing cost-out to date
Vendor | Contract | V1 budget | Renewal price | Costout |  | Committed summary | V1 budget | Renewal price | Costout
China Telecom Global Limited | AWS Network Circuit - Singapore to Shanghai | 31644 | 0 | 31644 |  | 22 committed items | 1053476.7944 | 497452.12 | 556024.6744
Digital Maas Pty Ltd | SEO Tool - Premium Subscription | 33330.3616 | 0 | 33330.3616
Dragon Metrics Limited | Dragon Metrics Subscription – Enterprise (Weekly ranking update) | 13440 | 0 | 13440
Happy Scribe | 0 | 588 | 0 | 588
Walkme for SAP | 0 | 187065.6 | 0 | 187065.6
Xtremepush Ltd | 0 | 5000 | 0 | 5000
Survey Monkey | 0 | 2.8457 | 0 | 2.8457
ContactMonkey | Outlook Add-In | 44383.56 | 21315 | 23068.56
Microway (Vyond) | Vyond Professional Annual - Single User | 4748.9171 | 0 | 4748.9171
App Samurai Limited | Storyly | 16835.05 | 0 | 16835.05
Creatify Lab Inc | Creatify Unlimited Team Plan (10 seats) | 18158.9 | 13921 | 4237.9
LinkedIn Singapore Pte Ltd | LinkedIn Talent Insights - Commerical ProServ (213 inv # 51110651342 ) | 354869.79 | 166469 | 188400.79
Similarweb Australia Pty Ltd | PRO Service - Digital Marketing Suite - Ultimate (Aus Contract) | 145598 | 141000 | 4598
Realtimeboard Inc. dba Miro | Miro - Enterprise License Plan 200 users | 89342.25 | 81676 | 7666.25
Adjust GmbH | Adjust Core - 1,000,000 Conversions | 21602.37 | 16705 | 4897.37
Data#3 Limited | Last Pass Subscription (Password Software Mgt) IAM Team | 20822.12 | 20822.12 | 0
APNIC Pty Ltd | Annual Membership | 2116 | 1709 | 407
Interactive Pty Ltd | Hardware Maintenance Renewal | 29440 | 27511 | 1929
Vimeo.com, INC | Vimeo Custom - Entry Level (44645097) | 12185.9 | 6116 | 6069.9
Data#3 Limited | TechSmith Camtasia licenses | 300.42 | 208 | 92.42
WP Engine | Hosting services, Secure Hosting Growth Plan | 12400.71 | 0 | 12400.71
Interactive Pty Ltd | UPS Maintenance Renewal | 9602 | 0 | 9602
Upcoming licensing vendors
Vendor | Contract | Contract date | V1 budget | Renewal price | Costout | Licensing summary | V1 budget | Renewal price | Costout
Freepik Company, SL | Freepik Premium+ Yearly | 06-Aug-26 | 10897.62 | 10897.62 | 0 | 63 uncommitted items | 6177955.6367 | 6039658.2592 | 137741.5967
EPI-USE Australia Pty Ltd | SuccessFactor Support - for global payroll integrations | 08-Sep-26 | 6959.34 | 6959.34 | 0
Insight Enterprises Australia Pty Ltd | Cerberus FTP Server (Not in Budget) | 11-Sep-26 | 4000 | 3928.96 | 71.04
Data#3 Limited | Adobe 1yr Licenses (2xCC) | 12-Sep-26 | 3496.56 | 0 | 3496.56
Data#3 Limited | Adobe 1yr Licenses (9xCC,1xAP) | 12-Sep-26 | 16764.09 | 0 | 16764.09
MightyHive AU PTY LTD | GA4 360 License | 30-Sep-26 | 83410.76 | 86000 | -2589.24
IP2Location | IP2Location Web Service (5,000,000 Credits) | 03-Oct-26 | 1771.24 | 1771.24 | 0
Maxmind Inc | IP address geolocation using accurate GeoIP® data. | 09-Oct-26 | 2558.56 | 2558.56 | 0
AWS Marketplace - Cloudec | Managed Services | 02-Nov-26 | 63000 | 63000 | 0
Voucherify P.S.A | Discount Code Software | 14-Nov-26 | 62507 | 62507 | 0
Award Force Pty Ltd | Awards Management Platform - to Manage Award Programs | 28-Nov-26 | 15442.02 | 15442.02 | 0
Learning Seat Pty Ltd | Litmos Content, ANZ Compl Ed Standalone | 29-Nov-26 | 22489.93 | 22489.93 | 0
Lucid Software Inc. | Lucide Suite x 83 | 30-Nov-26 | 55533.21 | 55533.21 | 0
Hello Teams Pty Ltd | HO - Australia | 01-Dec-26 | 44854.09 | 44854.09 | 0
Elemenator | 0 | 04-Dec-26 | 0 | 142.4 | -142.4
Appointlet | 0 | 08-Dec-26 | 16000 | 10780.5 | 5219.5
Sap Australia Pty Ltd | BTP Enterprise Agreement (213BTI) | 08-Dec-26 | 38169.86 | 38169.86 | 0
FRAUDWATCH INTERNATIONAL PTY LTD | Digital Brand Protection | 12-Dec-26 | 72737.12 | 72737.12 | 0
FastSpring | Numbeo API Basic Plan - living database | 15-Dec-26 | 7767.45 | 6000 | 1767.45
Vimeo.com, INC | Video sharing platform (IELTS) | 16-Dec-26 | 513 | 513 | 0
One Trust Australia Pty Ltd | GRC Tooling Cloud License - Risk Management | 17-Dec-26 | 83640.9 | 83640.9 | 0
AWS Marketplace - Splunk | Splunk Cloud Subscription | 22-Dec-26 | 819389.08 | 819389.08 | 0
AWS Marketplace - Splunk | Splunk Observability | 22-Dec-26 | 114542.94 | 144542.94 | -30000
Adobe Systems Software Ireland Limited | Marketo - Student Placement (Year 1- 1.2M, Year 2- $1.5M, Year 3- $1.7M) | 31-Dec-26 | 1806000 | 1806000 | 0
Adobe Systems Software Ireland Limited |  | 31-Dec-26 | 76651.4367 | 0 | 76651.4367
CISO Lens Pty Ltd | CISO Lens Membership - Simon Cowley, Rosie, AMG | 31-Dec-26 | 74680.82 | 74680.82 | 0
Ionic Inc. | 2 seats 2 concurrent builds 1.3M updates - IDP IELTS | 31-Dec-26 | 24773.62 | 13440 | 11333.62
Sap Australia Pty Ltd | SAP C4C V2 POC | 31-Dec-26 | 10185 | 0 | 10185
AWS Marketplace - Marketo | Marketo Engage | 05-Jan-27 | 836817.43 | 836817.43 | 0
Burst Training and Design | 19 x Articulate 360 TEAMs Annual Subscription - (Tech 2 licenses). | 14-Jan-27 | 43880.53 | 43880.53 | 0
Wordfence | idpielts.me, iknow.ielts.idp.com | 14-Jan-27 | 678.87 | 678.87 | 0
Screaming Frog | 0 | 19-Jan-27 | 2474.14 | 2474.14 | 0
Hubspot Australia PTY LTD | HubSpot - Marketing Hub Starter+G58 | 20-Jan-27 | 0 | 0 | 0
IP2Location | IP2Proxy Web Service (500,000 Credits) | 20-Jan-27 | 1788.49 | 1788.49 | 0
Supermetrics | Supermetrics - Hub | 21-Jan-27 | 85828.33 | 85828.33 | 0
Apple Inc. | DC Apple Developer Account - IDP Connect (Lower enviroment) | 25-Jan-27 | 420 | 179.5068 | 0
TeamViewer Germany GmbH | Remote access tool | 22-Feb-27 | 8702 | 8702 | 0
ZOHO Corporation | Site24x7 | 09-Mar-27 | 3088.36 | 0 | 3088.36
Mentimeter | 2 x Mentimeter pro licenses | 12-Mar-27 | 500 | 880 | -380
Time Target Pty Ltd | Humanforce T&A system for AU/NZ, | 16-Mar-27 | 75140.08 | 75140.08 | 0
C A Technology Pty Ltd (CAMMS) | CAMMS GRC Tool | 30-Mar-27 | 116104.27 | 116104.27 | 0
Apple Inc. | DC Apple Developer Account | 31-Mar-27 | 420 | 104.7123 | 0
UXCam Inc. | Mobile App analytics tool | 03-Apr-27 | 40335.34 | 40335.34 | 0
IPQS | IPQS SMB+ Enterprise Feature with Monthly IP Lookup (75,000) | 20-Apr-27 | 24960 | 24960 | 0
AWS Marketplace – Docker Inc | SW subscription Docker Business Plan | 27-Apr-27 | 23040 | 23040 | 0
CSC Corporate Domains, Inc. | Domain Registrations | 30-Apr-27 | 50400 | 30518.48 | 19881.52
Equinix Australia Pty Ltd | Saas - data center services | 30-Apr-27 | 52500 | 52500 | 0
DataEDO | Dataedo Starter (3 editors + unlimited viewers / community users) | 04-May-27 | 13600 | 13600 | 0
Mobbin.com | 0 | 09-May-27 | 0 | 691.2 | -691.2
ExpressVPN | 0 | 13-May-27 | 0 | 162.14 | -162.14
Interactive Pty Ltd | IBM Hardware and Software Maintenance Renewal (25%) | 17-May-27 | 158909.97 | 158909.97 | 0
Interactive Pty Ltd | IBM Hardware and Software Maintenance Renewal (75%) | 17-May-27 | 566888.67 | 566888.67 | 0
Convert Insights Inc. | Convert A/B testing Enterprise Plan | 21-May-27 | 41901.42 | 41901.42 | 0
Zoom Video Communications Inc | Zoom Licenses | 31-May-27 | 131371.72 | 131371.72 | 0
Import.io | SaaS Premium Plan (1M Query) | 01-Jun-27 | 45000 | 16000 | 29000
Figma, Inc. | Organization Full seats x 15 | 02-Jun-27 | 16929.2 | 16929.2 | 0
SonarSource SA | Quote_SonarQube Enterprise Edition Up to 10M Lines of Code | 04-Jun-27 | 86189.59 | 86189.59 | 0
ElevenLabs | Elevenlabs Enterprise Subscription - AI Voice | 11-Jun-27 | 0 | 0 | 0
Ahrefs Pte Ltd | Ahrefs Enterprise user Yearly | 30-Jun-27 | 20000 | 60752 | -40752
AWS Marketplace – IBM Software | IBM Cloudability Subscription renwal by Cloudec | 0 | 75000 | 40000 | 35000
Connect Managed Services (UK) Ltd | Service to Connect MTN’s SIP service to IDP’s PureCloud Software (Genesys Cloud) in Ghana (weconnect) | 0 | 0 | 0 | 0
TPG Telecom | Blanket PO for FY27 Monthly Invoices | 0 | 116179.08 | 116179.08 | 0
Verona Labs | WP Statistics Premium - Single Site - analytics plugin we use for iKnow | 0 | 172.5 | 172.5 | 0
Consumption cost-out to date
Vendor | Contract | V1 budget | Renewal price | Costout |  | Committed summary | V1 budget | Renewal price | Costout
No committed consumption items | [5 empty] | 0 committed items | 0 | 0 | 0
Upcoming consumption vendors
Vendor | Contract | V1 budget | Renewal price | Costout |  | Upcoming summary | V1 budget | Renewal price | Costout
Amazon Web Services Australia Pty Ltd |  | 5687336 | 5687336 | 0 |  | 24 uncommitted items | 7659712.8426 | 7658815.84 | 897.0026
AWS Marketplace - Anthropic PBC |  | 302217 | 302217 | 0
AWS Marketplace - ClamAV | BucketAV Software | 3630 | 3630 | 0
AWS Marketplace - N2WS | Aws Backups | 9600 | 9600 | 0
AWS Marketplace – NGINX Software | Load balancer | 15000 | 15000 | 0
Beijing Sinnet Technology Co., Ltd. |  | 31886.8426 | 31886.84 | 0.0025894
BitTitan |  | 497 | 0 | 497
Bulk SMS | SMS Alerts for PRTG it.accounts@idp.com www.bulksms.com | 0 | 0 | 0
Civica Pty Ltd |  | 973271.2 | 973271.2 | 0
Google Australia Pty Ltd | DC, Google Workspaces, IELTS - James Rich | 24000 | 24000 | 0
Google Australia Pty Ltd | Google Recaptcha | 2000 | 2000 | 0
Growthbook | Growthbook Cloud x 4 | 3024 | 3024 | 0
Gupshup |  | 14000 | 14000 | 0
Interactive Pty Ltd | UPS Servicing | 40000 | 40000 | 0
IVE Group Australia Pty Ltd |  | 296008 | 296008 | 0
LiveAgent | Service Desk platform the IELTS Customer Support Team | 20620.8 | 20620.8 | 0
Mapbox Inc | Location Data Platform - 3 accounts (SP, DM, LT) | 18000 | 18000 | 0
OpenAI |  | 100000 | 100000 | 0
SafetyCulture (iAuditor) |  | 11550 | 11550 | 0
Sinch Australia Pty Ltd | CPaaS | 42000 | 42000 | 0
Sinch UK Ltd. | CPaaS | 28000 | 28000 | 0
Stackify LLC |  | 7200 | 7200 | 0
Upstream Print Solutions Pty Ltd |  | 29472 | 29472 | 0
Zapier | Zapier - Pro Plan | 400 | 0 | 400
New Spend cost-out to date
Vendor | Contract | V1 budget | Renewal price | Costout |  | Committed summary | V1 budget | Renewal price | Costout
No committed new spend items | [5 empty] | 0 committed items | 0 | 0 | 0
Upcoming new spend vendors
Vendor | Contract | V1 budget | Renewal price | Costout |  | Upcoming summary | V1 budget | Renewal price | Costout
Contenful Nine Tail Personalisation |  | 100000 | 100000 | 0 |  | 10 uncommitted items | 458748.67 | 458748.67 | 0
Envato Elements |  | 7830 | 7830 | 0
Google support |  | 875 | 875 | 0
LLM |  | 10000 | 10000 | 0
NaturalReader |  | 1377 | 1377 | 0
New EA Tool |  | 80000 | 80000 | 0
NOOSR |  | 2000 | 2000 | 0
SANS |  | 50000 | 50000 | 0
Smartly IO |  | 186666.67 | 186666.67 | 0
TBC |  | 20000 | 20000 | 0
Microsoft cost-out to date
Vendor | Contract | V1 budget | Renewal price | Costout |  | Committed summary | V1 budget | Renewal price | Costout
No committed Microsoft items | [5 empty] | 0 committed items | 0 | 0 | 0
Upcoming Microsoft vendors
Vendor | Contract | V1 budget | Renewal price | Costout |  | Upcoming summary | V1 budget | Renewal price | Costout
Data#3 Limited | M365 (342) + O365 (310) Education Licenses | 9951.694 | 0 | 9951.694 |  | 22 uncommitted items | 8342612.51 | 8283551.07 | 59061.44
Data#3 Limited | Info River | 5359.7358 | 0 | 5359.7358
Insight Enterprises Australia Pty Ltd | Microsoft 365 Copilot x 200 | 113148 | 113148 | 0
Insight Enterprises Australia Pty Ltd | Microsoft 365 Copilot x 128 | 66087.33 | 66087.33 | 0
Insight Enterprises Australia Pty Ltd | Office 365 x Extra Storage x 15000 | 105300 | 105300 | 0
Insight Enterprises Australia Pty Ltd | Windows 365 Enterprise 4 vCPU, 16 GB, 128 GB x 20 | 32601.6 | 32601.6 | 0
Insight Enterprises Australia Pty Ltd | Windows 365 Enterprise 8 vCPU, 32 GB, 256 GB x 15 | 93340.8 | 93340.8 | 0
Insight Enterprises Australia Pty Ltd | Microsoft Visual Studio Pro MSDN ALng LSA | 0 | 0 | 0
Microsoft Pty Ltd |  | 243750 | 0 | 243750
Microsoft Pty Ltd | AZURE montly charges | 121394.16 | 121394.16 | 0
Microsoft Pty Ltd | Defender | 302982.0164 | 302982.02 | -0.0035616
Microsoft Pty Ltd | Enterprise Agreement (Corp Portion 30%) | 2052892.6321 | 2052892.63 | 0.0020548
Microsoft Pty Ltd | Enterprise Agreement (SP Portion 70%) | 4790082.8048 | 4790082.8 | 0.0047671
Microsoft Pty Ltd | Intune licence | 156240 | 156240 | 0
Microsoft Pty Ltd | Licenses and Software Assurance (Corp Portion 30%) | 8257.445 | 8257.44 | 0.0049973
Microsoft Pty Ltd | Licenses and Software Assurance (SP Portion 70%) | 19259.3717 | 19259.37 | 0.0016603
Microsoft Pty Ltd | Reservations | 29236.7198 | 29236.72 | -0.00021918
Microsoft Pty Ltd | SQL Server (Corp Portion 30%) | 43215.1092 | 43215.11 | -0.00075205
Microsoft Pty Ltd | SQL Server (SP Portion 70%) | 100835.2479 | 100835.25 | -0.0021192
Microsoft Pty Ltd | Teams Software | 11134.4627 | 11134.46 | 0.0026849
Microsoft Pty Ltd | Windows 10 ESU | 37543.3846 | 37543.38 | 0.0046154
Silverleaf Solutions Australia Pty Ltd | Microsoft EA Advisory | 0 | 200000 | -200000

## Snapshot 10-8
IT Simplification — FY27 Cost-out Dashboard
Actual savings achieved, remaining opportunity and timing by quarter
V1 BUDGET |  |  | ENTERED RENEWAL PRICE |  |  | NET IDENTIFIED COSTOUT |  | FINALISED POSITIVE COSTOUT
23692506.4576 |  |  | 23175361.5502 |  |  | 516589.1266 |  | 292654.7744
The tracked V1 budget is $23,692,506 and entered renewal prices total $23,175,362. The signed net identified costout in Column J is $516,589. Of the $793,413 gross positive costout identified, $292,655 is finalised (36.9%); $276,824 is separately classified as budget variance / reclassification.
QUARTERLY BUDGET, RENEWAL AND COSTOUT OUTLOOK
Metric | Q1 FY27 | Q2 FY27 | Q3 FY27 | Q4 FY27 | Unscheduled | FY27 Total
V1 budget | 844008.1728 | 3477136.3067 | 1175842.5 | 1272025.91 | 16923493.5682 | 23692506.4576
Entered renewal price | 778444.601 | 3402121.7 | 1172578.3592 | 1264749.73 | 16557467.16 | 23175361.5502
Net identified costout | 65563.5718 | 75014.6067 | 2708.36 | 7276.18 | 366026.4082 | 516589.1266
Finalised positive costout | 21586.8128 | 0 | 0 | 0 | 271067.9616 | 292654.7744
Unfinalised positive costout | 48673.349 | 105157.0067 | 3088.36 | 48881.52 | 294958.4532 | 500758.6888
Budget variance / reclassification | 4696.59 | 30142.4 | 380 | 41605.34 | 200000.0067 | 276824.3367
CATEGORY BUDGET, RENEWAL AND COSTOUT OUTLOOK
Category | V1 budget | Entered renewal price | Net identified costout | Finalised positive costout | Unfinalised positive costout | Budget variance / reclassification
Licensing | 7231432.4311 | 6774245.9702 | 456630.6801 | 292654.7744 | 240800.2356 | 76824.33
Consumption | 7659712.8426 | 7658815.84 | 897.0026 | 0 | 897.0026 | 0
New Spend | 458748.67 | 458748.67 | 0 | 0 | 0 | 0
Microsoft | 8342612.5139 | 8283551.07 | 59061.4439 | 0 | 259061.4506 | 200000.0067
Total | 23692506.4576 | 23175361.5502 | 516589.1266 | 292654.7744 | 500758.6888 | 276824.3367
Definitions: Net identified costout = the signed total of Column J across Licensing, Consumption, New Spend and Microsoft. Gross positive costout = positive Column J only. Finalised positive costout = positive Column J where Finalised? is Y. Budget variance / reclassification = the absolute value of negative Column J. Entered renewal price sums values currently populated in Column I. Data note: 7 tracked renewal-price cells are blank, covering $91,963 of V1 budget.
Licensing cost-out to date
Vendor | Contract | V1 budget | Renewal price | Costout |  | Committed summary | V1 budget | Renewal price | Costout
App Samurai Limited | Storyly | 16835.05 | 0 | 16835.05 |  | 9 committed items | 292654.7744 | 0 | 292654.7744
China Telecom Global Limited | AWS Network Circuit - Singapore to Shanghai | 31644 | 0 | 31644
Digital Maas Pty Ltd | SEO Tool - Premium Subscription | 33330.3616 | 0 | 33330.3616
Dragon Metrics Limited | Dragon Metrics Subscription – Enterprise (Weekly ranking update) | 13440 | 0 | 13440
Happy Scribe | 0 | 588 | 0 | 588
Microway (Vyond) | Vyond Professional Annual - Single User | 4748.9171 | 0 | 4748.9171
Survey Monkey | 0 | 2.8457 | 0 | 2.8457
Walkme for SAP | 0 | 187065.6 | 0 | 187065.6
Xtremepush Ltd | 0 | 5000 | 0 | 5000
Upcoming licensing vendors
Vendor | Contract | Contract date | V1 budget | Renewal price | Costout | Licensing summary | V1 budget | Renewal price | Costout
ContactMonkey | Outlook Add-In | 20-Jul-26 | 44383.56 | 23520 | 20863.56 | 76 uncommitted items | 6938777.6567 | 6774245.9702 | 163975.9056
Creatify Lab Inc | Creatify Unlimited Team Plan (10 seats) | 31-Jul-26 | 18158.9 | 16616.641 | 1542.259
Freepik Company, SL | Freepik Premium+ Yearly | 06-Aug-26 | 10897.62 | 10897.62 | 0
LinkedIn Singapore Pte Ltd | LinkedIn Talent Insights - Commerical ProServ (213 inv # 51110651342 ) | 07-Aug-26 | 354869.79 | 354869.79 | 0
Similarweb Australia Pty Ltd | PRO Service - Digital Marketing Suite - Ultimate (Aus Contract) | 21-Aug-26 | 145598 | 137028 | 8570
Realtimeboard Inc. dba Miro | Miro - Enterprise License Plan 200 users | 30-Aug-26 | 89342.25 | 91449.6 | -2107.35
Adjust GmbH | Adjust Core - 1,000,000 Conversions | 31-Aug-26 | 21602.37 | 16705 | 4897.37
EPI-USE Australia Pty Ltd | SuccessFactor Support - for global payroll integrations | 08-Sep-26 | 6959.34 | 6959.34 | 0
Insight Enterprises Australia Pty Ltd | Cerberus FTP Server (Not in Budget) | 11-Sep-26 | 4000 | 3928.96 | 71.04
Data#3 Limited | Adobe 1yr Licenses (2xCC) | 12-Sep-26 | 3496.56 | 3496.56 | 0
Data#3 Limited | Adobe 1yr Licenses (9xCC,1xAP) | 12-Sep-26 | 16764.09 | 16764.09 | 0
Data#3 Limited | Last Pass Subscription (Password Software Mgt) IAM Team | 12-Sep-26 | 20822.12 | 8500 | 12322.12
APNIC Pty Ltd | Annual Membership | 30-Sep-26 | 2116 | 1709 | 407
MightyHive AU PTY LTD | GA4 360 License | 30-Sep-26 | 83410.76 | 86000 | -2589.24
Interactive Pty Ltd | Hardware Maintenance Renewal | 02-Oct-26 | 29440 | 29440 | 0
IP2Location | IP2Location Web Service (5,000,000 Credits) | 03-Oct-26 | 1771.24 | 1771.24 | 0
Vimeo.com, INC | Vimeo Custom - Entry Level (44645097) | 06-Oct-26 | 12185.9 | 12185.9 | 0
Maxmind Inc | IP address geolocation using accurate GeoIP® data. | 09-Oct-26 | 2558.56 | 2558.56 | 0
Data#3 Limited | TechSmith Camtasia licenses | 11-Oct-26 | 300.42 | 300.42 | 0
WP Engine | Hosting services, Secure Hosting Growth Plan | 24-Oct-26 | 12400.71 | 12400.71 | 0
Interactive Pty Ltd | UPS Maintenance Renewal | 31-Oct-26 | 9602 | 9602 | 0
AWS Marketplace - Cloudec | Managed Services | 02-Nov-26 | 63000 | 63000 | 0
Voucherify P.S.A | Discount Code Software | 14-Nov-26 | 62507 | 62507 | 0
Award Force Pty Ltd | Awards Management Platform - to Manage Award Programs | 28-Nov-26 | 15442.02 | 15442.02 | 0
Learning Seat Pty Ltd | Litmos Content, ANZ Compl Ed Standalone | 29-Nov-26 | 22489.93 | 22489.93 | 0
Lucid Software Inc. | Lucide Suite x 83 | 30-Nov-26 | 55533.21 | 55533.21 | 0
Hello Teams Pty Ltd | HO - Australia | 01-Dec-26 | 44854.09 | 44854.09 | 0
Elemenator | 0 | 04-Dec-26 | 0 | 142.4 | -142.4
Appointlet | 0 | 08-Dec-26 | 16000 | 10780.5 | 5219.5
Sap Australia Pty Ltd | BTP Enterprise Agreement (213BTI) | 08-Dec-26 | 38169.86 | 38169.86 | 0
FRAUDWATCH INTERNATIONAL PTY LTD | Digital Brand Protection | 12-Dec-26 | 72737.12 | 72737.12 | 0
FastSpring | Numbeo API Basic Plan - living database | 15-Dec-26 | 7767.45 | 6000 | 1767.45
Vimeo.com, INC | Video sharing platform (IELTS) | 16-Dec-26 | 513 | 513 | 0
One Trust Australia Pty Ltd | GRC Tooling Cloud License - Risk Management | 17-Dec-26 | 83640.9 | 83640.9 | 0
AWS Marketplace - Splunk | Splunk Cloud Subscription | 22-Dec-26 | 819389.08 | 819389.08 | 0
AWS Marketplace - Splunk | Splunk Observability | 22-Dec-26 | 114542.94 | 144542.94 | -30000
Adobe Systems Software Ireland Limited | Marketo - Student Placement (Year 1- 1.2M, Year 2- $1.5M, Year 3- $1.7M) | 31-Dec-26 | 1806000 | 1806000 | 0
Adobe Systems Software Ireland Limited |  | 31-Dec-26 | 76651.4367 | 0 | 76651.4367
CISO Lens Pty Ltd | CISO Lens Membership - Simon Cowley, Rosie, AMG | 31-Dec-26 | 74680.82 | 74680.82 | 0
Ionic Inc. | 2 seats 2 concurrent builds 1.3M updates - IDP IELTS | 31-Dec-26 | 24773.62 | 13440 | 11333.62
Sap Australia Pty Ltd | SAP C4C V2 POC | 31-Dec-26 | 10185 | 0 | 10185
AWS Marketplace - Marketo | Marketo Engage | 05-Jan-27 | 836817.43 | 836817.43 | 0
Burst Training and Design | 19 x Articulate 360 TEAMs Annual Subscription - (Tech 2 licenses). | 14-Jan-27 | 43880.53 | 43880.53 | 0
Wordfence | idpielts.me, iknow.ielts.idp.com | 14-Jan-27 | 678.87 | 678.87 | 0
Screaming Frog | 0 | 19-Jan-27 | 2474.14 | 2474.14 | 0
Hubspot Australia PTY LTD | HubSpot - Marketing Hub Starter+G58 | 20-Jan-27 | 0 | 0 | 0
IP2Location | IP2Proxy Web Service (500,000 Credits) | 20-Jan-27 | 1788.49 | 1788.49 | 0
Supermetrics | Supermetrics - Hub | 21-Jan-27 | 85828.33 | 85828.33 | 0
Apple Inc. | DC Apple Developer Account - IDP Connect (Lower enviroment) | 25-Jan-27 | 420 | 179.5068 | 0
TeamViewer Germany GmbH | Remote access tool | 22-Feb-27 | 8702 | 8702 | 0
ZOHO Corporation | Site24x7 | 09-Mar-27 | 3088.36 | 0 | 3088.36
Mentimeter | 2 x Mentimeter pro licenses | 12-Mar-27 | 500 | 880 | -380
Time Target Pty Ltd | Humanforce T&A system for AU/NZ, | 16-Mar-27 | 75140.08 | 75140.08 | 0
C A Technology Pty Ltd (CAMMS) | CAMMS GRC Tool | 30-Mar-27 | 116104.27 | 116104.27 | 0
Apple Inc. | DC Apple Developer Account | 31-Mar-27 | 420 | 104.7123 | 0
UXCam Inc. | Mobile App analytics tool | 03-Apr-27 | 40335.34 | 40335.34 | 0
IPQS | IPQS SMB+ Enterprise Feature with Monthly IP Lookup (75,000) | 20-Apr-27 | 24960 | 24960 | 0
AWS Marketplace – Docker Inc | SW subscription Docker Business Plan | 27-Apr-27 | 23040 | 23040 | 0
CSC Corporate Domains, Inc. | Domain Registrations | 30-Apr-27 | 50400 | 30518.48 | 19881.52
Equinix Australia Pty Ltd | Saas - data center services | 30-Apr-27 | 52500 | 52500 | 0
DataEDO | Dataedo Starter (3 editors + unlimited viewers / community users) | 04-May-27 | 13600 | 13600 | 0
Mobbin.com | 0 | 09-May-27 | 0 | 691.2 | -691.2
ExpressVPN | 0 | 13-May-27 | 0 | 162.14 | -162.14
Interactive Pty Ltd | IBM Hardware and Software Maintenance Renewal (25%) | 17-May-27 | 158909.97 | 158909.97 | 0
Interactive Pty Ltd | IBM Hardware and Software Maintenance Renewal (75%) | 17-May-27 | 566888.67 | 566888.67 | 0
Convert Insights Inc. | Convert A/B testing Enterprise Plan | 21-May-27 | 41901.42 | 41901.42 | 0
Zoom Video Communications Inc | Zoom Licenses | 31-May-27 | 131371.72 | 131371.72 | 0
Import.io | SaaS Premium Plan (1M Query) | 01-Jun-27 | 45000 | 16000 | 29000
Figma, Inc. | Organization Full seats x 15 | 02-Jun-27 | 16929.2 | 16929.2 | 0
SonarSource SA | Quote_SonarQube Enterprise Edition Up to 10M Lines of Code | 04-Jun-27 | 86189.59 | 86189.59 | 0
ElevenLabs | Elevenlabs Enterprise Subscription - AI Voice | 11-Jun-27 | 0 | 0 | 0
Ahrefs Pte Ltd | Ahrefs Enterprise user Yearly | 30-Jun-27 | 20000 | 60752 | -40752
AWS Marketplace – IBM Software | IBM Cloudability Subscription renwal by Cloudec | 0 | 75000 | 40000 | 35000
Connect Managed Services (UK) Ltd | Service to Connect MTN’s SIP service to IDP’s PureCloud Software (Genesys Cloud) in Ghana (weconnect) | 0 | 0 | 0 | 0
TPG Telecom | Blanket PO for FY27 Monthly Invoices | 0 | 116179.08 | 116179.08 | 0
Verona Labs | WP Statistics Premium - Single Site - analytics plugin we use for iKnow | 0 | 172.5 | 172.5 | 0
Consumption cost-out to date
Vendor | Contract | V1 budget | Renewal price | Costout |  | Committed summary | V1 budget | Renewal price | Costout
No committed consumption items | [5 empty] | 0 committed items | 0 | 0 | 0
Upcoming consumption vendors
Vendor | Contract | V1 budget | Renewal price | Costout |  | Upcoming summary | V1 budget | Renewal price | Costout
Amazon Web Services Australia Pty Ltd |  | 5687336 | 5687336 | 0 |  | 24 uncommitted items | 7659712.8426 | 7658815.84 | 897.0026
AWS Marketplace - Anthropic PBC |  | 302217 | 302217 | 0
AWS Marketplace - ClamAV | BucketAV Software | 3630 | 3630 | 0
AWS Marketplace - N2WS | Aws Backups | 9600 | 9600 | 0
AWS Marketplace – NGINX Software | Load balancer | 15000 | 15000 | 0
Beijing Sinnet Technology Co., Ltd. |  | 31886.8426 | 31886.84 | 0.0025894
BitTitan |  | 497 | 0 | 497
Bulk SMS | SMS Alerts for PRTG it.accounts@idp.com www.bulksms.com | 0 | 0 | 0
Civica Pty Ltd |  | 973271.2 | 973271.2 | 0
Google Australia Pty Ltd | DC, Google Workspaces, IELTS - James Rich | 24000 | 24000 | 0
Google Australia Pty Ltd | Google Recaptcha | 2000 | 2000 | 0
Growthbook | Growthbook Cloud x 4 | 3024 | 3024 | 0
Gupshup |  | 14000 | 14000 | 0
Interactive Pty Ltd | UPS Servicing | 40000 | 40000 | 0
IVE Group Australia Pty Ltd |  | 296008 | 296008 | 0
LiveAgent | Service Desk platform the IELTS Customer Support Team | 20620.8 | 20620.8 | 0
Mapbox Inc | Location Data Platform - 3 accounts (SP, DM, LT) | 18000 | 18000 | 0
OpenAI |  | 100000 | 100000 | 0
SafetyCulture (iAuditor) |  | 11550 | 11550 | 0
Sinch Australia Pty Ltd | CPaaS | 42000 | 42000 | 0
Sinch UK Ltd. | CPaaS | 28000 | 28000 | 0
Stackify LLC |  | 7200 | 7200 | 0
Upstream Print Solutions Pty Ltd |  | 29472 | 29472 | 0
Zapier | Zapier - Pro Plan | 400 | 0 | 400
New Spend cost-out to date
Vendor | Contract | V1 budget | Renewal price | Costout |  | Committed summary | V1 budget | Renewal price | Costout
No committed new spend items | [5 empty] | 0 committed items | 0 | 0 | 0
Upcoming new spend vendors
Vendor | Contract | V1 budget | Renewal price | Costout |  | Upcoming summary | V1 budget | Renewal price | Costout
Contenful Nine Tail Personalisation |  | 100000 | 100000 | 0 |  | 10 uncommitted items | 458748.67 | 458748.67 | 0
Envato Elements |  | 7830 | 7830 | 0
Google support |  | 875 | 875 | 0
LLM |  | 10000 | 10000 | 0
NaturalReader |  | 1377 | 1377 | 0
New EA Tool |  | 80000 | 80000 | 0
NOOSR |  | 2000 | 2000 | 0
SANS |  | 50000 | 50000 | 0
Smartly IO |  | 186666.67 | 186666.67 | 0
TBC |  | 20000 | 20000 | 0
Microsoft cost-out to date
Vendor | Contract | V1 budget | Renewal price | Costout |  | Committed summary | V1 budget | Renewal price | Costout
No committed Microsoft items | [5 empty] | 0 committed items | 0 | 0 | 0
Upcoming Microsoft vendors
Vendor | Contract | V1 budget | Renewal price | Costout |  | Upcoming summary | V1 budget | Renewal price | Costout
Data#3 Limited | M365 (342) + O365 (310) Education Licenses | 9951.694 | 0 | 9951.694 |  | 22 uncommitted items | 8342612.51 | 8283551.07 | 59061.44
Data#3 Limited | Info River | 5359.7358 | 0 | 5359.7358
Insight Enterprises Australia Pty Ltd | Microsoft 365 Copilot x 200 | 113148 | 113148 | 0
Insight Enterprises Australia Pty Ltd | Microsoft 365 Copilot x 128 | 66087.33 | 66087.33 | 0
Insight Enterprises Australia Pty Ltd | Office 365 x Extra Storage x 15000 | 105300 | 105300 | 0
Insight Enterprises Australia Pty Ltd | Windows 365 Enterprise 4 vCPU, 16 GB, 128 GB x 20 | 32601.6 | 32601.6 | 0
Insight Enterprises Australia Pty Ltd | Windows 365 Enterprise 8 vCPU, 32 GB, 256 GB x 15 | 93340.8 | 93340.8 | 0
Insight Enterprises Australia Pty Ltd | Microsoft Visual Studio Pro MSDN ALng LSA | 0 | 0 | 0
Microsoft Pty Ltd |  | 243750 | 0 | 243750
Microsoft Pty Ltd | AZURE montly charges | 121394.16 | 121394.16 | 0
Microsoft Pty Ltd | Defender | 302982.0164 | 302982.02 | -0.0035616
Microsoft Pty Ltd | Enterprise Agreement (Corp Portion 30%) | 2052892.6321 | 2052892.63 | 0.0020548
Microsoft Pty Ltd | Enterprise Agreement (SP Portion 70%) | 4790082.8048 | 4790082.8 | 0.0047671
Microsoft Pty Ltd | Intune licence | 156240 | 156240 | 0
Microsoft Pty Ltd | Licenses and Software Assurance (Corp Portion 30%) | 8257.445 | 8257.44 | 0.0049973
Microsoft Pty Ltd | Licenses and Software Assurance (SP Portion 70%) | 19259.3717 | 19259.37 | 0.0016603
Microsoft Pty Ltd | Reservations | 29236.7198 | 29236.72 | -0.00021918
Microsoft Pty Ltd | SQL Server (Corp Portion 30%) | 43215.1092 | 43215.11 | -0.00075205
Microsoft Pty Ltd | SQL Server (SP Portion 70%) | 100835.2479 | 100835.25 | -0.0021192
Microsoft Pty Ltd | Teams Software | 11134.4627 | 11134.46 | 0.0026849
Microsoft Pty Ltd | Windows 10 ESU | 37543.3846 | 37543.38 | 0.0046154
Silverleaf Solutions Australia Pty Ltd | Microsoft EA Advisory | 0 | 200000 | -200000